## task
document_identifier | work_breakdown_structure | name
1 | 1 | TECHNIPFMC – LABSEA
2 | 1.1 | Replanejamento 03.03
3 | 1.2 | INICIO DA OBRA - REUNIÃO DE KICK OFF
4 | 1.2.1 | Contratação de Containers
5 | 1.2.2 | Aquisição de materiais para execução de isolamento da área
6 | 1.2.3 | Emissão do Pedido de Compra - Perfil W 250 x 85 (Estacas Metálicas)
7 | 1.2.4 | Aquisição de materiais e entrega para manufaturamento
8 | 1.3 | EXECUÇÃO DA OBRA
9 | 1.3.1 | Mobilização
10 | 1.3.1.1 | Execução de Tapume
11 | 1.3.1.2 | Montagem do Canteiro de Obras
12 | 1.3.2 | Locação da Obra
13 | 1.3.2.1 | Retirada de piso intertravado
14 | 1.3.2.2 | Montagem do gabarito
15 | 1.3.2.3 | Locação Topográfica
16 | 1.3.3 | Fundação
17 | 1.3.3.1 | Mobilização do Equipamento de Bate Estaca
18 | 1.3.3.2 | Entrega e descarga dos perfis metálicos W 250 x 85 (Estacas Metálicas)
19 | 1.3.3.3 | Execução da cravação das estacas metálicas (Parte 1 de 2)
20 | 1.3.3.4 | Execução da cravação das estacas metálicas (Parte 2 de 2)
21 | 1.3.3.5 | Execução de blocos sobre estacas
22 | 1.3.4 | Infra Estrutura
23 | 1.3.4.1 | Execução de Vigas Baldrames
24 | 1.3.4.2 | Execução de Laje de piso e canaletas
25 | 1.3.5 | Estrutura Metálica
26 | 1.3.5.1 | Fabricação
27 | 1.3.5.2 | Transporte e descarga na obra
28 | 1.3.5.3 | Montagem
Página 1
29 | 1.3.6 | Cobertura
30 | 1.3.6.1 | Instalação de Calhas
31 | 1.3.6.2 | Instalação de Telhas
32 | 1.3.6.3 | Instalação de rufos
33 | 1.3.7 | Obras Civis - Vedações / Revestimentos
34 | 1.3.7.1 | Alvenaria
35 | 1.3.7.1.1 | Alvenaria fachada 01 - 3,60
36 | 1.3.7.1.2 | Alvenaria fachada 02 - 3,60
37 | 1.3.7.1.3 | Alvenaria fachada 03 - 3,60
38 | 1.3.7.1.4 | Alvenaria fachada 04 - 3,60
39 | 1.3.7.1.5 | Alvenaria fachada 04 complemento
40 | 1.3.7.1.6 | Alvenaria fachada 02 e 03 complemento
41 | 1.3.7.1.7 | Alvenaria interna - 3,60
42 | 1.3.7.1.8 | Alvenaria fachada 01 complemento
43 | 1.3.7.2 | Chapisco & Reboco - interno
44 | 1.3.7.2.1 | Parede 01
45 | 1.3.7.2.2 | Parede 02
46 | 1.3.7.2.3 | Parede 03
47 | 1.3.7.2.4 | Parede 04
48 | 1.3.7.2.5 | Alvenaria interna lado 01
49 | 1.3.7.2.6 | Alvenaria interna lado 02
50 | 1.3.7.3 | Chapisco & Reboco - externo (apenas onde e pintura)
51 | 1.3.7.3.1 | Fachada 01
52 | 1.3.7.3.2 | Fachada 02 e 03
53 | 1.3.7.3.3 | Fachada 04
54 | 1.3.7.4 | Arremates / Requadrações
55 | 1.3.8 | Obras Civis - Acabamentos
56 | 1.3.8.1 | Revestimento Interno - Pintura
57 | 1.3.8.2 | Revestimento Externo - Pintura
58 | 1.3.8.3 | Revestimento Externo - Monocapa
59 | 1.3.8.4 | Forro acústico - Casa de Máquinas
Página 2
60 | 1.3.8.5 | Soleiras e Peitoris de granito
61 | 1.3.8.6 | Instalação de ACM
62 | 1.3.8.7 | Pintura Epóxi do piso
63 | 1.3.8.8 | Instalação das grelhas de aço no piso
64 | 1.3.9 | Esquadrias
65 | 1.3.9.1 | Porta de Vidro
66 | 1.3.9.2 | Janelas - Aluminío / Vidro
67 | 1.3.9.3 | Porta Corta - Fogo
68 | 1.3.9.4 | Porta Acústica
69 | 1.3.9.5 | Portão de entrada do Galpão - LABSEA
70 | 1.3.10 | Instalações Elétricas
71 | 1.3.10.1 | Execução da malha de aterramento
72 | 1.3.10.2 | SPDA (Sistema de Proteção contra Descargas Atmosféricas) - Interligação na estrutura metálica
73 | 1.3.10.3 | Acabamento do SPDA
74 | 1.3.10.4 | Infra estrutura de alimentadores elétricos
75 | 1.3.10.5 | Infra Estrutura de tubulações, leitos, eletrocalhas e perfilados
76 | 1.3.10.6 | Infra estrutura de alimentadores elétricos - prédio
77 | 1.3.10.7 | Passagem de cabos alimentadores
78 | 1.3.10.8 | Passagem de circuitos elétricos: iluminação e tomadas
79 | 1.3.10.9 | instalação de tomadas e interruptores
80 | 1.3.10.10 | Instalação de luminárias
81 | 1.3.10.11 | Instalação de quadros elétricos
82 | 1.3.10.12 | Instalação de No Break
83 | 1.3.11 | Instalações Hidráulicas
84 | 1.3.11.1 | Rede de drenagem externa
85 | 1.3.11.2 | Rede de água potável - piso
86 | 1.3.11.3 | Rede de drenagem interna
87 | 1.3.11.4 | Descidas de AP da cobertura
88 | 1.3.11.5 | Rede de água potável - parede
89 | 1.3.12 | Interfaces
Página 3
90 | 1.3.12.1 | Ponte rolante
91 | 1.3.12.1. | Finalização da estrutura da cobertura (Sem as terças)
92 | 1.3.12.1. | Finalização da estrutura da cobertura (Com terças e telhas)
93 | 1.3.12.2 | Climatização
94 | 1.3.12.2. | Liberação da montagem de dutos e equipamentos
95 | 1.3.13 | Recomposições - Áreas Externas
96 | 1.3.13.1 | Recompoisção de piso intertravado
97 | 1.3.13.2 | Recomposição de área verde
98 | 1.3.13.3 | Instalação de Gradil - Proteção dos Equip. de Ar Condicionado
99 | 1.3.13.4 | Demarcação de vagas
100 | 1.3.14 | Desmobilização
101 | 1.3.14.1 | Limpeza Geral / Desmobilização
Página 4

## task_time
schedule_duration | schedule_start | schedule_finish | planned_progress_percent | executed_progress_percent | deviation_percent | completion_percent
185 dias | Ter 04/11/25 | Ter 11/08/26 | 84,78 | 91,72 | 6,94 | 92%
0 dias | Ter 03/03/26 | Ter 03/03/26 | 0 | 0 | 0 | 0%
33 dias | Ter 04/11/25 | Seg 05/01/26 | 100 | 100 | 0 | 100%
4 dias | Ter 04/11/25 | Seg 10/11/25 | 100 | 100 | 0 | 100%
4 dias | Ter 04/11/25 | Seg 10/11/25 | 100 | 100 | 0 | 100%
1 dia | Ter 11/11/25 | Qua 12/11/25 | 100 | 100 | 0 | 100%
15 dias | Seg 01/12/25 | Seg 05/01/26 | 100 | 100 | 0 | 100%
180 dias | Ter 11/11/25 | Ter 11/08/26 | 84,19 | 91,39 | 7,2 | 91%
8 dias | Ter 11/11/25 | Seg 24/11/25 | 100 | 100 | 0 | 100%
7 dias | Ter 11/11/25 | Sex 21/11/25 | 100 | 100 | 0 | 100%
5 dias | Sex 14/11/25 | Seg 24/11/25 | 100 | 100 | 0 | 100%
7 dias | Ter 25/11/25 | Qui 04/12/25 | 100 | 100 | 0 | 100%
2 dias | Ter 25/11/25 | Qui 27/11/25 | 100 | 100 | 0 | 100%
1 dia | Sex 28/11/25 | Seg 01/12/25 | 100 | 100 | 0 | 100%
2 dias | Ter 02/12/25 | Qui 04/12/25 | 100 | 100 | 0 | 100%
20 dias | Sex 05/12/25 | Seg 19/01/26 | 100 | 100 | 0 | 100%
1 dia | Sex 05/12/25 | Seg 08/12/25 | 100 | 100 | 0 | 100%
1 dia | Ter 09/12/25 | Qua 10/12/25 | 100 | 100 | 0 | 100%
6 dias | Qua 10/12/25 | Qui 18/12/25 | 100 | 100 | 0 | 100%
7 dias | Sex 19/12/25 | Ter 13/01/26 | 100 | 100 | 0 | 100%
2 dias | Qua 14/01/26 | Seg 19/01/26 | 100 | 100 | 0 | 100%
25 dias | Ter 20/01/26 | Ter 24/02/26 | 100 | 100 | 0 | 100%
7 dias | Ter 20/01/26 | Qui 29/01/26 | 100 | 100 | 0 | 100%
17 dias | Sex 30/01/26 | Ter 24/02/26 | 100 | 100 | 0 | 100%
66 dias | Ter 06/01/26 | Sex 10/04/26 | 100 | 100 | 0 | 100%
44 dias | Ter 06/01/26 | Ter 10/03/26 | 100 | 100 | 0 | 100%
1 dia | Qua 11/03/26 | Qui 12/03/26 | 100 | 100 | 0 | 100%
18 dias | Seg 16/03/26 | Sex 10/04/26 | 100 | 100 | 0 | 100%
8 dias | Seg 06/04/26 | Qui 16/04/26 | 100 | 100 | 0 | 100%
2 dias | Seg 06/04/26 | Qua 08/04/26 | 100 | 100 | 0 | 100%
3 dias | Qui 09/04/26 | Ter 14/04/26 | 100 | 100 | 0 | 100%
2 dias | Ter 14/04/26 | Qui 16/04/26 | 100 | 100 | 0 | 100%
53 dias | Seg 11/05/26 | Qui 23/07/26 | 98,67 | 99,53 | 0,86 | 99%
33 dias | Seg 11/05/26 | Qui 25/06/26 | 100 | 100 | 0 | 100%
9 dias | Seg 11/05/26 | Sex 22/05/26 | 100 | 100 | 0 | 100%
10 dias | Seg 11/05/26 | Seg 25/05/26 | 100 | 100 | 0 | 100%
12 dias | Seg 11/05/26 | Qua 27/05/26 | 100 | 100 | 0 | 100%
10 dias | Seg 11/05/26 | Seg 25/05/26 | 100 | 100 | 0 | 100%
12 dias | Ter 26/05/26 | Qui 11/06/26 | 100 | 100 | 0 | 100%
12 dias | Ter 26/05/26 | Qui 11/06/26 | 100 | 100 | 0 | 100%
10 dias | Qui 28/05/26 | Qui 11/06/26 | 100 | 100 | 0 | 100%
10 dias | Qui 11/06/26 | Qui 25/06/26 | 100 | 100 | 0 | 100%
15 dias | Qui 11/06/26 | Qui 02/07/26 | 100 | 100 | 0 | 100%
3 dias | Sex 26/06/26 | Qua 01/07/26 | 100 | 100 | 0 | 100%
6 dias | Sex 12/06/26 | Seg 22/06/26 | 100 | 100 | 0 | 100%
4 dias | Qui 11/06/26 | Qua 17/06/26 | 100 | 100 | 0 | 100%
5 dias | Sex 12/06/26 | Sex 19/06/26 | 100 | 100 | 0 | 100%
4 dias | Sex 12/06/26 | Qui 18/06/26 | 100 | 100 | 0 | 100%
4 dias | Sex 26/06/26 | Qui 02/07/26 | 100 | 100 | 0 | 100%
16 dias | Seg 22/06/26 | Ter 14/07/26 | 100 | 100 | 0 | 100%
8 dias | Qui 02/07/26 | Ter 14/07/26 | 100 | 100 | 0 | 100%
8 dias | Qui 02/07/26 | Ter 14/07/26 | 100 | 100 | 0 | 100%
8 dias | Seg 22/06/26 | Qui 02/07/26 | 100 | 100 | 0 | 100%
25 dias | Qui 18/06/26 | Qui 23/07/26 | 91,5 | 97 | 5,5 | 97%
29 dias | Qua 01/07/26 | Ter 11/08/26 | 34,93 | 78,92 | 43,99 | 79%
13 dias | Qua 01/07/26 | Seg 20/07/26 | 100 | 97 | -3 | 97%
20 dias | Ter 14/07/26 | Ter 11/08/26 | 24,38 | 97 | 72,62 | 97%
10 dias | Seg 27/07/26 | Seg 10/08/26 | 0 | 100 | 100 | 100%
2 dias | Seg 20/07/26 | Qua 22/07/26 | 43,75 | 100 | 56,25 | 100%
5 dias | Qua 01/07/26 | Qua 08/07/26 | 100 | 100 | 0 | 100%
7 dias | Qui 23/07/26 | Seg 03/08/26 | 0 | 45 | 45 | 45%
8 dias | Qua 22/07/26 | Seg 03/08/26 | 0 | 0 | 0 | 0%
3 dias | Seg 03/08/26 | Qui 06/08/26 | 0 | 50 | 50 | 50%
22 dias | Qua 08/07/26 | Sex 07/08/26 | 80 | 25 | -55 | 25%
1 dia | Qua 08/07/26 | Qui 09/07/26 | 100 | 0 | -100 | 0%
6 dias | Qui 09/07/26 | Sex 17/07/26 | 100 | 0 | -100 | 0%
1 dia | Sex 17/07/26 | Seg 20/07/26 | 100 | 100 | 0 | 100%
1 dia | Qua 22/07/26 | Qui 23/07/26 | 0 | 100 | 100 | 100%
1 dia | Qui 06/08/26 | Sex 07/08/26 | 0 | 50 | 50 | 50%
143 dias | Seg 19/01/26 | Ter 11/08/26 | 74,36 | 96,88 | 22,52 | 97%
20 dias | Seg 19/01/26 | Seg 16/02/26 | 100 | 100 | 0 | 100%
10 dias | Qui 16/04/26 | Seg 04/05/26 | 100 | 100 | 0 | 100%
5 dias | Seg 13/07/26 | Seg 20/07/26 | 100 | 100 | 0 | 100%
22 dias | Ter 20/01/26 | Qui 19/02/26 | 100 | 100 | 0 | 100%
13 dias | Qui 25/06/26 | Ter 14/07/26 | 100 | 100 | 0 | 100%
10 dias | Ter 30/06/26 | Ter 14/07/26 | 100 | 100 | 0 | 100%
10 dias | Qua 15/07/26 | Qua 29/07/26 | 38,75 | 100 | 61,25 | 100%
6 dias | Qua 15/07/26 | Qui 23/07/26 | 64,58 | 100 | 35,42 | 100%
6 dias | Qui 23/07/26 | Sex 31/07/26 | 0 | 97,01 | 97,01 | 97%
3 dias | Qui 23/07/26 | Ter 28/07/26 | 0 | 100 | 100 | 100%
10 dias | Qua 22/07/26 | Qua 05/08/26 | 0 | 95 | 95 | 95%
3 dias | Qui 06/08/26 | Ter 11/08/26 | 0 | 0 | 0 | 0%
131 dias | Seg 19/01/26 | Sex 24/07/26 | 96,19 | 100 | 3,81 | 100%
20 dias | Seg 19/01/26 | Seg 16/02/26 | 100 | 100 | 0 | 100%
20 dias | Qui 22/01/26 | Qui 19/02/26 | 100 | 100 | 0 | 100%
20 dias | Seg 26/01/26 | Seg 23/02/26 | 100 | 100 | 0 | 100%
7 dias | Qua 17/06/26 | Sex 26/06/26 | 100 | 100 | 0 | 100%
15 dias | Sex 03/07/26 | Sex 24/07/26 | 79,17 | 100 | 20,83 | 100%
58 dias | Sex 10/04/26 | Sex 03/07/26 | 100 | 100 | 0 | 100%
5 dias | Sex 10/04/26 | Sex 17/04/26 | 100 | 100 | 0 | 100%
1 dia | Sex 10/04/26 | Seg 13/04/26 | 100 | 100 | 0 | 100%
1 dia | Qui 16/04/26 | Sex 17/04/26 | 100 | 100 | 0 | 100%
10 dias | Sex 19/06/26 | Sex 03/07/26 | 100 | 100 | 0 | 100%
10 dias | Sex 19/06/26 | Sex 03/07/26 | 100 | 100 | 0 | 100%
28 dias | Ter 23/06/26 | Sex 31/07/26 | 75,38 | 42,43 | -32,95 | 42%
14 dias | Ter 23/06/26 | Seg 13/07/26 | 100 | 100 | 0 | 100%
9 dias | Seg 13/07/26 | Sex 24/07/26 | 65,28 | 0 | -65,28 | 0%
5 dias | Seg 13/07/26 | Seg 20/07/26 | 100 | 0 | -100 | 0%
5 dias | Sex 24/07/26 | Sex 31/07/26 | 0 | 0 | 0 | 0%
8 dias | Qui 30/07/26 | Ter 11/08/26 | 0 | 0 | 0 | 0%
8 dias | Qui 30/07/26 | Ter 11/08/26 | 0 | 0 | 0 | 0%

## predecessor_relation
related_process | relating_process
1.1 | 4TI+69 dias
1.2.3 | 5TI+1 dia
1.2.4 | 5TI+14 dias
1.3.1.1 | 6II
1.3.1.2 | 10II+3 dias
1.3.2.1 | 11TI+1 dia
1.3.2.2 | 13TI+1 dia
1.3.2.3 | 14TI+1 dia
1.3.3.1 | 15TI+1 dia
1.3.3.2 | 17TI+1 dia
1.3.3.3 | 18
1.3.3.4 | 19II+7 dias
1.3.3.5 | 20TI+1 dia
1.3.4.1 | 21TI+1 dia
1.3.4.2 | 23TI+1 dia
1.3.5.1 | 7TI+1 dia
1.3.5.2 | 26TI+1 dia
1.3.5.3 | 27TI+2 dias
1.3.5.3 | 24
1.3.6.1 | 28II+14 dias
1.3.6.2 | 30TI+1 dia
1.3.6.3 | 31
1.3.7.1.1 | 31TI+17 dias
1.3.7.1.2 | 31TI+17 dias
1.3.7.1.3 | 31TI+17 dias
1.3.7.1.4 | 31TI+17 dias
1.3.7.1.5 | 35TI+1 dia
1.3.7.1.5 | 38TI+1
1.3.7.1.6 | 36TI+1 dia
1.3.7.1.7 | 37TI+1 dia
1.3.7.1.8 | 41
1.3.7.2.1 | 42TI+1 dia
1.3.7.2.1 | 35TI+1
1.3.7.2.2 | 40TI+1 dia
1.3.7.2.2 | 36TI+1
1.3.7.2.3 | 37TI+1 dia
1.3.7.2.3 | 41
1.3.7.2.4 | 39TI+1 dia
1.3.7.2.4 | 38TI+1
1.3.7.2.5 | 41TI+1 dia
1.3.7.2.6 | 48TI+1 dia
1.3.7.2.6 | 42TI+1
1.3.7.3.1 | 45
1.3.7.3.1 | 44TI+1 dia
1.3.7.3.2 | 53
1.3.7.3.2 | 45TI+1 dia
1.3.7.3.3 | 46
1.3.7.3.3 | 47TI+1 dia
1.3.7.4 | 46TI+1 dia
1.3.8.1 | 44
1.3.8.1 | 94II
1.3.8.2 | 52
1.3.8.2 | 51
1.3.8.2 | 53
1.3.8.3 | 57II+9 dias
1.3.8.4 | 56
1.3.8.4 | 94
1.3.8.5 | 44
1.3.8.6 | 54
1.3.8.7 | 56
1.3.8.7 | 59
1.3.8.8 | 62
1.3.9.1 | 60
1.3.9.2 | 65
1.3.9.3 | 66
1.3.9.4 | 67
1.3.9.4 | 59
1.3.9.5 | 68
1.3.9.5 | 63
1.3.10.1 | 21II+2 dias
1.3.10.2 | 32
1.3.10.3 | 96
1.3.10.3 | 72
1.3.10.4 | 71II+1 dia
1.3.10.5 | 42
1.3.10.6 | 75TT
1.3.10.7 | 76TI+1 dia
1.3.10.7 | 74
1.3.10.8 | 75TI+1 dia
1.3.10.9 | 78
1.3.10.9 | 56
1.3.10.10 | 78
1.3.10.10 | 59
1.3.10.11 | 54II
1.3.10.11 | 76
1.3.10.11 | 77II+5 dia
1.3.10.12 | 81TI+1 dia
1.3.11.1 | 21II+2 dias
1.3.11.2 | 84II+3 dias
1.3.11.3 | 85II+2 dias
1.3.11.4 | 32TI+42 dias
1.3.11.4 | 86
1.3.11.5 | 49TI+1 dia
1.3.11.5 | 85
1.3.12.1. | 28
1.3.12.1. | 32
1.3.12.2. | 48TI+1 dia
1.3.13.1 | 42TI+20 dias
1.3.13.2 | 96
1.3.13.3 | 96
1.3.13.4 | 98
1.3.13.4 | 97
1.3.14.1 | 99TT
1.3.14.1 | 58TT+1 dia

## successor_relation
relating_process | related_process
1.2.1 | 2TI+69 dias
1.2.2 | 6TI+1 dia
1.2.2 | 7TI+14 dias
1.2.3 | 10II
1.2.4 | 26TI+1 dia
1.3.1.1 | 11II+3 dias
1.3.1.2 | 13TI+1 dia
1.3.2.1 | 14TI+1 dia
1.3.2.2 | 15TI+1 dia
1.3.2.3 | 17TI+1 dia
1.3.3.1 | 18TI+1 dia
1.3.3.2 | 19
1.3.3.3 | 20II+7 dias
1.3.3.4 | 21TI+1 dia
1.3.3.5 | 23TI+1 dia
1.3.3.5 | 71II+2 dias
1.3.3.5 | 84
1.3.4.1 | 24TI+1 dia
1.3.4.2 | 28
1.3.5.1 | 27TI+1 dia
1.3.5.2 | 28TI+2 dias
1.3.5.3 | 91
1.3.5.3 | 30II+14 dias
1.3.6.1 | 31TI+1 dia
1.3.6.2 | 35TI+17 dias
1.3.6.2 | 36TI+17 dia
1.3.6.3 | 87TI+42 dias
1.3.6.3 | 92
1.3.6.3 | 72
1.3.7.1.1 | 39TI+1 dia
1.3.7.1.1 | 44TI+1 dia
1.3.7.1.2 | 40TI+1 dia
1.3.7.1.2 | 45TI+1 dia
1.3.7.1.3 | 41TI+1 dia
1.3.7.1.3 | 46TI+1 dia
1.3.7.1.4 | 47TI+1 dia
1.3.7.1.4 | 39TI+1 dia
1.3.7.1.5 | 47TI+1 dia
1.3.7.1.6 | 45TI+1 dia
1.3.7.1.7 | 42
1.3.7.1.7 | 48TI+1 dia
1.3.7.1.7 | 46
1.3.7.1.8 | 44TI+1 dia
1.3.7.1.8 | 49TI+1 dia
1.3.7.1.8 | 75
1.3.7.2.1 | 51TI+1 dia
1.3.7.2.1 | 56
1.3.7.2.1 | 60
1.3.7.2.2 | 51
1.3.7.2.2 | 52TI+1 dia
1.3.7.2.3 | 53
1.3.7.2.3 | 54TI+1 dia
1.3.7.2.4 | 53TI+1 dia
1.3.7.2.5 | 49TI+1 dia
1.3.7.2.5 | 94TI+1 dia
1.3.7.2.6 | 88TI+1 dia
1.3.7.3.1 | 57
1.3.7.3.2 | 57
1.3.7.3.3 | 52
1.3.7.3.3 | 57
1.3.7.4 | 81II
1.3.7.4 | 61
1.3.8.1 | 59
1.3.8.1 | 62
1.3.8.1 | 79
1.3.8.2 | 58II+9 dias
1.3.8.3 | 101TT+1 dia
1.3.8.4 | 62
1.3.8.4 | 80
1.3.8.4 | 68
1.3.8.5 | 65
1.3.8.7 | 63
1.3.8.8 | 69
1.3.9.1 | 66
1.3.9.2 | 67
1.3.9.3 | 68
1.3.9.4 | 69
1.3.9.5 | 101TT
1.3.10.1 | 74II+1 dia
1.3.10.2 | 73
1.3.10.3 | 101TT
1.3.10.4 | 77
1.3.10.5 | 78TI+1 dia
1.3.10.5 | 76TT
1.3.10.6 | 77TI+1 dia
1.3.10.6 | 81
1.3.10.7 | 81II+5 dias
1.3.10.8 | 79
1.3.10.8 | 80
1.3.10.9 | 101TT
1.3.10.10 | 101TT
1.3.10.11 | 82TI+1 dia
1.3.11.1 | 85II+3 dias
1.3.11.2 | 86II+2 dias
1.3.11.2 | 88
1.3.11.3 | 87
1.3.11.4 | 101TT
1.3.11.5 | 101TT+1 dia
1.3.12.1. | 101TT
1.3.12.1. | 101TT+1 dia
1.3.12.2. | 59
1.3.12.2. | 56II
1.3.13.1 | 97
1.3.13.1 | 73
1.3.13.1 | 98
1.3.13.2 | 101TT
1.3.13.2 | 99
1.3.13.3 | 99
1.3.13.4 | 101TT

## _facade_contract
facade_uri | facade_identifier | facade_name | ifc_class_name | instance_role | is_repeatable | field_uri | field_identifier | field_name | description | field_datatype | maps_from_header_field | maps_to_property | ifc_attribute_name | is_required | is_multivalued
http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskFacade | ifc_task_facade | IfcTask Facade | IfcTask | task | FALSE | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskDocumentIdentifierField | document_identifier | Document Identifier | Document-local task identifier captured in the tabular source row. | xsd:string | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/type.ttl#IdentifierField |  |  | FALSE | FALSE
http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskFacade | ifc_task_facade | IfcTask Facade | IfcTask | task | FALSE | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskWorkBreakdownStructureField | work_breakdown_structure | Work Breakdown Structure | Primary work breakdown structure code projected to the IFC task identification. | xsd:string | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/type.ttl#WorkBreakdownStructureField |  | Identification | FALSE | FALSE
http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskFacade | ifc_task_facade | IfcTask Facade | IfcTask | task | FALSE | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskNameField | name | Name | Primary task name projected to the IFC task name. | xsd:string | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/type.ttl#TaskNameField | https://schema.org/name | Name | FALSE | FALSE
http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskTimeFacade | ifc_task_time_facade | IfcTaskTime Facade | IfcTaskTime | task_time | FALSE | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskTimeDurationField | schedule_duration | Schedule Duration | Planned schedule duration projected to IfcTaskTime. | xsd:string | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/type.ttl#DurationField |  | ScheduleDuration | FALSE | FALSE
http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskTimeFacade | ifc_task_time_facade | IfcTaskTime Facade | IfcTaskTime | task_time | FALSE | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskTimeStartField | schedule_start | Schedule Start | Planned start date projected to IfcTaskTime. | xsd:string | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/type.ttl#StartDateField |  | ScheduleStart | FALSE | FALSE
http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskTimeFacade | ifc_task_time_facade | IfcTaskTime Facade | IfcTaskTime | task_time | FALSE | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskTimeFinishField | schedule_finish | Schedule Finish | Planned finish date projected to IfcTaskTime. | xsd:string | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/type.ttl#FinishDateField |  | ScheduleFinish | FALSE | FALSE
http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskTimeFacade | ifc_task_time_facade | IfcTaskTime Facade | IfcTaskTime | task_time | FALSE | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskTimePlannedProgressField | planned_progress_percent | Planned Progress Percent | Planned progress percentage captured from the source row. | xsd:string | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/type.ttl#PlannedProgressPercentField |  |  | FALSE | FALSE
http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskTimeFacade | ifc_task_time_facade | IfcTaskTime Facade | IfcTaskTime | task_time | FALSE | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskTimeExecutedProgressField | executed_progress_percent | Executed Progress Percent | Executed progress percentage captured from the source row. | xsd:string | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/type.ttl#ExecutedProgressPercentField |  |  | FALSE | FALSE
http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskTimeFacade | ifc_task_time_facade | IfcTaskTime Facade | IfcTaskTime | task_time | FALSE | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskTimeDeviationField | deviation_percent | Deviation Percent | Deviation percentage captured from the source row. | xsd:string | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/type.ttl#DeviationPercentField |  |  | FALSE | FALSE
http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskTimeFacade | ifc_task_time_facade | IfcTaskTime Facade | IfcTaskTime | task_time | FALSE | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcTaskTimeCompletionField | completion_percent | Completion Percent | Completion percentage projected to IfcTaskTime completion. | xsd:string | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/type.ttl#CompletionPercentField |  | Completion | FALSE | FALSE
http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcRelSequencePredecessorFacade | ifc_rel_sequence_predecessor_facade | IfcRelSequence Predecessor Facade | IfcRelSequence | predecessor_relation | TRUE | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcRelSequencePredecessorCurrentTaskField | related_process | Related Process | Current row task reference projected as the related process of the predecessor relation. | xsd:string | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/type.ttl#WorkBreakdownStructureField |  | RelatedProcess | FALSE | FALSE
http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcRelSequencePredecessorFacade | ifc_rel_sequence_predecessor_facade | IfcRelSequence Predecessor Facade | IfcRelSequence | predecessor_relation | TRUE | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcRelSequencePredecessorReferenceField | relating_process | Relating Process | Predecessor task references projected as the relating process of the sequence relation. | xsd:string | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/type.ttl#PredecessorsField |  | RelatingProcess | FALSE | TRUE
http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcRelSequenceSuccessorFacade | ifc_rel_sequence_successor_facade | IfcRelSequence Successor Facade | IfcRelSequence | successor_relation | TRUE | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcRelSequenceSuccessorCurrentTaskField | relating_process | Relating Process | Current row task reference projected as the relating process of the successor relation. | xsd:string | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/type.ttl#WorkBreakdownStructureField |  | RelatingProcess | FALSE | FALSE
http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcRelSequenceSuccessorFacade | ifc_rel_sequence_successor_facade | IfcRelSequence Successor Facade | IfcRelSequence | successor_relation | TRUE | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/facade.ttl#IfcRelSequenceSuccessorReferenceField | related_process | Related Process | Successor task references projected as the related process of the sequence relation. | xsd:string | http://datacenter.app.br/ontology/bsi/element/ifc_work_schedule/type.ttl#SuccessorsField |  | RelatedProcess | FALSE | TRUE

## _provenance
LABSEA — IfcWorkSchedule workbook
Property | Value
Source schedule | CRONOGRAMA - TFMC LABSEA REV04 20.07.pdf
Instantiated artifact | __instantiated__.json
Facade source | https://github.com/Brasidata/brasidatacenter/blob/master/ontology/bsi/element/ifc_work_schedule/facade.ttl
Facade blob SHA | a2550b38cb25b99825da6a181a2f067f76d3e419
Element | IfcWorkSchedule
Source state | __semanticized__
Row groups | 109
IFC instances | 419
Instance role | Rows
task | 105
task_time | 101
predecessor_relation | 104
successor_relation | 109
Total | 419
Contract rule: worksheet names use facade:instanceRole; columns use each FacadeField schema:identifier in the exact order declared by facade.ttl. All source values remain lexical strings, as declared by fieldDatatype xsd:string. No GlobalId, status, milestone or other non-facade column was invented.